## Schedule
PROJECT Schedule | [25 empty] | Created by
| Project Start: |  | 2021-01-01
| Display Week: |  | 4
[6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15
[6 empty] | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21
TASK | ASSIGNED TO | % Complete | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Plan
task 1.1 | Project Manager | 100% | 2021-01-01 | 2021-01-04 | 2
task 1.2 | Architect | 100% | 2021-01-05 | 2021-01-11 | 5
task 1.3 | Architect | 25% | 2021-01-12 | 2021-01-13 | 2
task 1.4 | Consultant | 100% | 2021-01-14 | 2021-01-19 | 4
task 1.5 | Senior Eng | 100% | 2021-01-20 | 2021-01-20 | 1
task 1.6 | Senior Eng | 40% | 2021-01-21 | 2021-02-01 | 7
task 1.7 | Senior Eng |  | 2021-02-02 | 2021-02-02 | 1
task 1.8 | Senior Eng | 40% | 2021-02-03 | 2021-02-09 | 5
task 1.9 | Senior Eng |  | 2021-02-10 | 2021-02-10 | 1
task 1.10 | Engineer |  | 2021-02-11 | 2021-02-11 | 1
task 1.11 | Engineer | 35% | 2021-02-12 | 2021-02-16 | 3
task 1.11 | Engineer |  | 2021-02-17 | 2021-02-17 | 1
Design
task 2.1 | Project Manager | 50% | 2021-02-18 | 2021-02-19 | 2
task 2.2 | Consultant |  | 2021-02-22 | 2021-02-22 | 1
task 2.3 | Consultant |  | 2021-02-23 | 2021-02-23 | 1
task 2.4 | Consultant |  | 2021-02-24 | 2021-02-24 | 1
task 2.5 | Senior Eng |  | 2021-02-25 | 2021-02-25 | 1
task 2.6 | Senior Eng |  | 2021-02-26 | 2021-02-26 | 1
task 2.7 | Senior Eng | 75% | 2021-03-01 | 2021-03-04 | 4
task 2.8 | Senior Eng |  | 2021-03-05 | 2021-03-09 | 3
task 2.9 | Senior Eng |  | 2021-03-10 | 2021-03-11 | 2
task 2.10 | Senior Eng |  | 2021-03-12 | 2021-03-12 | 1
task 2.11 | Engineer |  | 2021-03-16 | 2021-03-16 | 1
Build
task 3.1 | Senior Eng |  | 2021-03-17 | 2021-03-23 | 5
task 3.2 | Senior Eng |  | 2021-03-24 | 2021-03-29 | 4
task 3.3 | Senior Eng |  | 2021-03-30 | 2021-04-01 | 3
task 3.4 | Senior Eng | 50% | 2021-04-06 | 2021-04-07 | 2
task 3.5 | Senior Eng |  | 2021-04-08 | 2021-04-08 | 1
task 3.6 | Senior Eng |  | 2021-04-08 | 2021-04-08 | 1
task 3.7 | Senior Eng |  | 2021-04-09 | 2021-04-09 | 1
task 3.8 | Senior Eng |  | 2021-04-12 | 2021-04-12 | 1
task 3.9 | Senior Eng |  | 2021-04-13 | 2021-04-13 | 1
task 3.10 | Engineer |  | 2021-04-14 | 2021-04-14 | 1
task 3.11 | Engineer |  | 2021-04-15 | 2021-04-16 | 2
task 3.12 | Engineer |  | 2021-04-19 | 2021-04-19 | 1
task 3.13 | Engineer |  | 2021-04-20 | 2021-04-20 | 1
Implement
task 4.1 | Senior Eng |  | 2021-04-21 | 2021-04-21 | 1
task 4.2 | Senior Eng |  | 2021-04-22 | 2021-04-22 | 1
task 4.3 | Senior Eng |  | 2021-04-23 | 2021-04-23 | 1
task 4.4 | Senior Eng |  | 2021-04-26 | 2021-04-26 | 1
task 4.5 | Senior Eng |  | 2021-04-27 | 2021-04-27 | 1
task 4.6 | Senior Eng |  | 2021-04-28 | 2021-04-28 | 1
task 4.7 | Senior Eng |  | 2021-04-29 | 2021-04-29 | 1
task 4.8 | Senior Eng |  | 2021-04-30 | 2021-04-30 | 1
task 4.9 | Senior Eng |  | 2021-05-03 | 2021-05-03 | 1
task 4.10 | Engineer |  | 2021-05-04 | 2021-05-04 | 1
task 4.11 | Engineer |  | 2021-05-05 | 2021-05-05 | 1
task 4.12 | Engineer |  | 2021-05-06 | 2021-05-06 | 1
Handover
task 5.1 | Senior Eng |  | 2021-05-07 | 2021-05-10 | 2
task 5.2 | Senior Eng |  | 2021-05-11 | 2021-05-12 | 2
task 5.3 | Engineer |  | 2021-05-13 | 2021-05-17 | 3
task 5.4 | Engineer |  | 2021-05-18 | 2021-05-21 | 4
task 5.5 | Engineer |  | 2021-05-24 | 2021-05-28 | 5
task 5.6 | SDM |  | 2021-05-31 | 2021-06-07 | 6
task 5.7 | SDM |  | 2021-06-08 | 2021-06-17 | 7
task 5.8 | SDM |  | 2021-06-18 | 2021-06-29 | 8
task 5.9 | SDM |  | 2021-06-30 | 2021-07-12 | 9
Note on E10: Please add days in the days column, do not change dates

## Holidays
Holidays and Other Non Working Days
Date | Description
2019-12-25 | Christmas Day
2020-12-25 | Christmas Day
2021-12-25 | Christmas Day
2022-12-25 | Christmas Day
2023-12-25 | Christmas Day
2024-12-25 | Christmas Day
2019-12-26 | Boxing Day
2020-12-27 | Boxing Day
2021-12-26 | Boxing Day
2022-12-26 | Boxing Day
2023-12-26 | Boxing Day
2024-12-26 | Boxing Day
2019-01-01 | New Years Day
2020-01-01 | New Years Day
2021-01-01 | New Years Day
2022-01-01 | New Years Day
2023-01-01 | New Years Day
2019-02-14 | Valentines Day
2021-01-26 | Australia Day
2021-03-15 | Labour Day
2021-04-25 | Anzac Day
2021-04-02 | Good Friday
2021-04-05 | Easter Monday
2021-06-14 | Queens Birthday

## Settings (hidden)
WEEKEND Option
| Weekend String | 0000011
| Monday | 0 | Display Weeks
| Tuesday | 0 | 0
| Wednesday | 0 | 1
| Thursday | 0 | 2
| Friday | 0 | 3
| Saturday | 1 | 4
| Sunday | 1 | 5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53